## PTBC Themes
PTBC ID | Theme | Category | Source spec | Resolution gate | Gate basis | FG-04 configurable | Status | Decision owner | AHDA-approved value | Working baseline (not approved) | Linked tasks | Earliest linked wave | Evidence
PTBC-001 | Approval authority matrix - who may approve what, at what value | Approval & Authority | WF-11; Blueprint v2.0 Section 11 | Before UAT | Approval mechanics build generically; routing cannot be validated in UAT without the matrix | Yes - FG-04 published configuration | Open | AHDA Business Sponsor / Portfolio Office |  |  | TASK-034, TASK-035 | W1 | Open Questions OQ-005; TASK-034 Participation Amendment (FG-04 owns the approval authority matrix)
PTBC-002 | Project lifecycle fast-track rule - whether Under Review may be skipped | Lifecycle & Workflow | WF-01; Blueprint v2.0 Sections 5, 9; ICD-02 | Before Build/Integration Build | Changes the Project state machine; a transition not built cannot be added without re-approving live projects | No | Open | AHDA PMO / Business Sponsor |  |  | TASK-041 | W2 | TASK-041 Acceptance Criteria: 'a Project cannot skip Under Review unless an explicitly authorized fast-track rule exists (else flagged as Open Question, PTBC-002)'
PTBC-003 | External entity onboarding and eligibility authority | External Participation | WF-13 | Before Build/Integration Build | Determines who may hold an external grant and on what basis; drives the authorization model, not a threshold | Partly - participation mode per project is FG-04 configuration | Partially Resolved | AHDA Business Sponsor / AHDA PMO | Entity-initiated project draft with AHDA approval; R04 Project Manager is employer-neutral, scoped to the entity's own project (ADR-013, AHDA PMO 20 Sep 2026) |  | TASK-066, TASK-067, TASK-068 | W5 | OQ-007; ADR-013; TASK-068 Detailed Description
PTBC-004 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-005 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-006 | Milestone achievement evidence policy - mandatory evidence per milestone category | Evidence & Documentation | WF-05; WF-12; ICD-04 | Before UAT | UI and backend enforce whatever policy is published; until it exists the UI labels evidence optional-pending-policy rather than accepting an unvalidated submission | Yes - FG-04 published configuration | Open | AHDA PMO |  |  | TASK-050, TASK-051 | W4 | TASK-051 Acceptance Criteria: 'the evidence configured as mandatory for the milestone's category (once PTBC-006/PTBC-019 are resolved)'
PTBC-007 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-008 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-009 | Change materiality and monetary thresholds - band boundaries for cost, schedule and scope | Approval & Authority | WF-08 | Before UAT | ADR-016 fixes three bands and the highest-band rule; only the boundary values are outstanding, and routing cannot be scored in UAT without them | Yes - FG-04 published configuration per governance profile | Partially Resolved | AHDA Business Sponsor / Portfolio Office | Shape only: three bands across cost, schedule and scope; a change takes the highest band any dimension triggers; changes accumulate against the active baseline (ADR-016) |  | TASK-027, TASK-034, TASK-060, TASK-061, TASK-106 | W1 | OQ-005; OQ-013 (cited by TASK-106, row absent from the Open Questions sheet); ADR-016
PTBC-010 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-011 | Mandatory formal audit event classes | Audit & Logging | FG-06; Blueprint v2.0 Section 18 | Before Build/Integration Build | The audit store is append-only; an event class not captured at build cannot be reconstructed later | No | Open | AHDA Cybersecurity / PMO |  |  | TASK-033, TASK-073 | W1 | TASK-033 Detailed Description: 'Emit formal Audit events (FG-06, PTBC-011/029)'
PTBC-012 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-013 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-014 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-015 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-016 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-017 | Risk and issue probability/impact matrix - level descriptions, boundaries, 5x5 mapping, rating labels | Risk & Issue | WF-06; WF-07 | Before UAT | ADR-011 fixed the record structure before P9 build; the values are pinned per assessment version, so they can be published later without rewriting history | Yes - FG-04 published configuration, version-pinned at assessment time | Partially Resolved | AHDA Business Sponsor / Risk & Portfolio Office | Shape only: impact is multi-dimensional (cost, schedule, reputation and at least one operational dimension), five levels per dimension, same scale for risks and issues (ADR-011, AHDA gate 19 Sep 2026) |  | TASK-027, TASK-034, TASK-055, TASK-056, TASK-057, TASK-059 | W1 | OQ-006; ADR-011; TASK-055 Detailed Description
PTBC-018 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-019 | PENDING - not recoverable from available sources; cited jointly with PTBC-006 as a milestone-evidence precondition | Evidence & Documentation | PENDING (Blueprint v2.0 Appendix F.2) | Before UAT | Assigned the same gate as PTBC-006, with which the workbook cites it as a single precondition | PENDING | Open | AHDA PMO |  |  | TASK-051 | W4 | TASK-051 Acceptance Criteria: '(once PTBC-006/PTBC-019 are resolved)'
PTBC-020 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-021 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-022 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-023 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-024 | KPI formulas and targets | Financial & KPI | WF-14; Blueprint v2.0 Section 8.1 | Before UAT | Target versions are immutable and measurements pin the version effective when recorded, so targets can be published later; UAT cannot validate KPI status without them | Yes - FG-04 published configuration; approved Target Versions | Open | AHDA Business Sponsor / AHDA PMO |  |  | TASK-034, TASK-052, TASK-053 | W1 | OQ-006 (positional reading: OQ-006 lists risk matrix, KPI formulas/targets, financial thresholds against PTBC-017, PTBC-024, PTBC-025 in that order - confirm against Appendix F.2)
PTBC-025 | Financial condition and variance thresholds | Financial & KPI | WF-14; Blueprint v2.0 Section 8.1 | Before UAT | Condition is a derived display state over stored figures; it can be configured after the figures exist, but UAT cannot score it without the thresholds | Yes - FG-04 published configuration | Open | AHDA Business Sponsor / AHDA Finance |  |  | TASK-034, TASK-052, TASK-053 | W1 | OQ-006 (positional reading - see PTBC-024)
PTBC-026 | PENDING - not recoverable from available sources; within the cybersecurity governance group PTBC-026 to PTBC-030 | Cybersecurity Governance | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | AHDA Cybersecurity |  |  | TASK-010 | W0 | TASK-010 Validation Checks: 'confirm PTBC-026 through PTBC-030 (cybersecurity governance themes) are each linked to a matrix row'
PTBC-027 | MFA and privileged-access policy, and the step-up authentication trigger list | Cybersecurity Governance | FG-03; Blueprint v2.0 Section 22 | Before UAT | ADR-010 fixes that step-up applies to privileged and sensitive actions; the mechanism is built now and the trigger list is configuration | Yes - trigger list configurable | Partially Resolved | AHDA Cybersecurity | Step-up authentication applies to privileged and sensitive actions (ADR-010, AHDA gate 19 Sep 2026) |  | TASK-010, TASK-029 | W0 | TASK-029 Detailed Description: 'per PTBC-027, pending AHDA's exact MFA/PAM policy confirmation'; TASK-029 Gate Decision Applied
PTBC-028 | PENDING - not recoverable from available sources; within the cybersecurity governance group PTBC-026 to PTBC-030 | Cybersecurity Governance | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | AHDA Cybersecurity |  |  | TASK-010 | W0 | TASK-010 Validation Checks
PTBC-029 | SIEM forwarding subset - which audit and security event classes are forwarded | Cybersecurity Governance | FG-06; Blueprint v2.0 Sections 18, 22 | Before Production | Forwarding is deployment configuration over events already captured under PTBC-011; it does not change what is stored | Yes - forwarding rules configurable | Open | AHDA Cybersecurity |  |  | TASK-010, TASK-033, TASK-083 | W0 | TASK-033 Detailed Description: 'forwarding a defined subset to SIEM per PTBC-029'
PTBC-030 | PENDING - not recoverable from available sources; within the cybersecurity governance group PTBC-026 to PTBC-030 | Cybersecurity Governance | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | AHDA Cybersecurity |  |  | TASK-010 | W0 | TASK-010 Validation Checks
PTBC-031 | Nafath use case scope and identity data-minimisation boundary | Integration | WF-13; FG-05; RFP integration requirement | Before Build/Integration Build | The minimisation decision determines which identity attributes are stored; storing first and deleting later is not a remedy for personal data | No | Partially Resolved | AHDA IT (Identity) / AHDA Cybersecurity | In scope for external entity users, identity verification at onboarding only, never internal sign-in; a persistent sign-in session follows verification (ADR-007, ADR-013) |  | TASK-013, TASK-068 | W1 | OQ-007; ADR-007; ADR-013; Environment and Secrets, NAFATH_CLIENT_ID: 'subject to PTBC-031 scope confirmation'
PTBC-032 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-033 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-034 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-035 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-036 | Authoritative directory and role-sync model | Identity & Access | FG-03; ADM-041 | Before Build/Integration Build | Determines whether platform roles are inherited from directory groups or assigned in the platform - a structural choice in the authorization model | No | Resolved | AHDA IT (Identity) | AHDA's existing directory with SSO. The directory is authoritative for department, manager and job title. Platform roles are assigned in the platform and are NOT inherited from directory groups (ADR-007, AHDA gate 19 Sep 2026) |  | TASK-013, TASK-028 | W1 | TASK-028 Detailed Description: 'PTBC-036: authoritative directory and sync model is Open Question pending AHDA IT input'; TASK-028 Gate Decision Applied; ADR-007
PTBC-037 | Operational alert thresholds - availability, freshness, queue backlog, reconciliation mismatch | Observability & Operations | FG-05; Blueprint v2.0 Section 17.1 | Before Production | Alerting is an operational target over a built mechanism; it changes no stored data and no functional UAT outcome | Yes - alert thresholds configurable | Open | AHDA IT / DevOps Lead |  |  | TASK-075, TASK-091, TASK-092 | W2 | TASK-092 Detailed Description: 'once PTBC-037/046 values are confirmed by AHDA'
PTBC-038 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-039 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-040 | Target accessibility conformance level | Non-Functional | Blueprint v2.0 (non-functional requirements) | Before UAT | The audit is scored against the level; the level must be fixed before the P15 audit, not after its findings are known | No | Open (baseline proposed) | AHDA Business Sponsor |  | WCAG 2.1 Level AA - delivery-team position, proposed for AHDA confirmation, not an AHDA decision | TASK-084, TASK-087 | W1 | OQ-010; TASK-087 Gate Decision Applied; Release Checklist 'Accessibility Audit Findings Closed'
PTBC-041 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-042 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-043 | Platform performance and NFR thresholds | Non-Functional | Blueprint v2.0 (non-functional requirements); RFP capacity statement | Before UAT | Load testing and the release gate are scored against the thresholds; the indexing baseline is sized to them | No | Open (baseline proposed) | AHDA Business Sponsor / AHDA IT |  | 150 named users, 25 concurrent, 50 at peak - delivery-team position from the brief's capacity assumption, proposed for AHDA confirmation | TASK-026, TASK-084, TASK-086 | W1 | OQ-010; TASK-086 Detailed Description; Release Checklist 'Performance/Load Test Within Target'
PTBC-044 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-045 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-046 | PENDING - not recoverable from available sources; cited jointly with PTBC-037 as an operational threshold value | Observability & Operations | PENDING (Blueprint v2.0 Appendix F.2) | Before Production | Assigned the same gate as PTBC-037, with which the workbook cites it as a single precondition | PENDING | Unpopulated | AHDA IT / DevOps Lead |  |  | TASK-092 | W6 | TASK-092 Detailed Description: 'once PTBC-037/046 values are confirmed by AHDA'
PTBC-047 | PENDING - not recoverable from available sources | PENDING | PENDING (Blueprint v2.0 Appendix F.2) | PENDING | Cannot be assigned without the theme subject | PENDING | Unpopulated | PENDING |  |  |  |  | No reference to this ID exists in the Implementation work workbook (all five sheets, read 2026-09-20)
PTBC-048 | Backup retention period and disaster-recovery objectives (RPO/RTO) | Infrastructure & DR | Blueprint v2.0 Section 22; AHDA IT business continuity plan | Before Production | The mechanism is built with the period configurable; the release gate 'Backup & DR Restore Drill Passed' is scored on the values before go-live | Yes - retention period configurable | Partially Resolved | AHDA IT (RPO/RTO); AHDA Cybersecurity + Records (retention) | RPO 1 hour; RTO 4 to 6 hours (AHDA IT business continuity plan, AHDA gate 19 Sep 2026, recorded in ADR-001 and OQ-003). Retention period: no value - still open |  | TASK-020, TASK-023, TASK-093 | W1 | OQ-003; ADR-001; TASK-020 and TASK-023 Gate Decision Applied; docs/rtm/step-14b-rtm-findings-closure.md F-03

## Task Cross-Reference
Task ID | Task name | Phase | Wave (per TASK-003) | PTBC ID | Link status | PTBC-gated value the task touches
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | PTBC-026 | Present in workbook | Cybersecurity control matrix must link each of PTBC-026 to PTBC-030 to a control row
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | PTBC-027 | Present in workbook | Cybersecurity control matrix must link each of PTBC-026 to PTBC-030 to a control row
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | PTBC-028 | Present in workbook | Cybersecurity control matrix must link each of PTBC-026 to PTBC-030 to a control row
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | PTBC-029 | Present in workbook | Cybersecurity control matrix must link each of PTBC-026 to PTBC-030 to a control row
TASK-010 | Ratify Cybersecurity Control Overlay Mapping (CS-001-033) | P1 | W0 | PTBC-030 | Present in workbook | Cybersecurity control matrix must link each of PTBC-026 to PTBC-030 to a control row
TASK-013 | Author Environment Variable Templates per Environment | P2 | W1 | PTBC-031 | Required workbook edit | NAFATH_CLIENT_ID and the other Nafath variables exist only for the use case PTBC-031 confirms
TASK-013 | Author Environment Variable Templates per Environment | P2 | W1 | PTBC-036 | Required workbook edit | AD_LDAP_URL, AD_BIND_DN and AD_BIND_PASSWORD follow the directory model fixed by PTBC-036
TASK-020 | Provision Managed AlloyDB for PostgreSQL with Backup & Encryption | P3 | W1 | PTBC-048 | Present in workbook | Backup frequency, point-in-time recovery window and retention period
TASK-023 | Define Backup, Restore & Disaster Recovery Runbook | P3 | W1 | PTBC-048 | Present in workbook | RPO/RTO pass-fail criteria for the restore drill; retention period field in the runbook
TASK-026 | Define Indexing Strategy for Query, Filter, Sort & Pagination Paths | P4 | W1 | PTBC-043 | Required workbook edit | Index sizing and the query-plan review are run at the capacity figures PTBC-043 fixes
TASK-027 | Build Seed Data & Data-Integrity Validation Scripts | P4 | W1 | PTBC-009 | Required workbook edit | Seed data includes materiality band values once they are approved
TASK-027 | Build Seed Data & Data-Integrity Validation Scripts | P4 | W1 | PTBC-017 | Required workbook edit | Risk and issue scales are seeded generically; boundary values outstanding
TASK-028 | Integrate AD/LDAP and SSO Authentication | P5 | W1 | PTBC-036 | Present in workbook | Directory authority and group/claim-to-role mapping
TASK-029 | Implement MFA & Privileged Access Controls | P5 | W1 | PTBC-027 | Present in workbook | MFA/PAM policy and the step-up authentication trigger list
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | PTBC-011 | Present in workbook | Which event classes are captured as formal Audit events
TASK-033 | Implement Authentication & Access Audit Logging | P5 | W1 | PTBC-029 | Present in workbook | Which audit event classes are forwarded to SIEM
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | PTBC-001 | Required workbook edit | FG-04 publishes the approval authority matrix as versioned configuration
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | PTBC-009 | Required workbook edit | FG-04 publishes materiality band values per governance profile
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | PTBC-017 | Required workbook edit | FG-04 publishes the probability/impact matrix that WF-06 and WF-07 pin per assessment
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | PTBC-024 | Required workbook edit | FG-04 publishes KPI rule configuration and approved target versions
TASK-034 | Build Master Data & Configuration Service (FG-04 Backend) | P6 | W1 | PTBC-025 | Required workbook edit | FG-04 publishes financial condition and variance threshold configuration
TASK-035 | Build Shared Approval Framework (WF-11 Backend) | P6 | W2 | PTBC-001 | Required workbook edit | Approval routing and authority evaluation configuration
TASK-041 | Build Project Creation & Registration (WF-01 Backend) | P7 | W2 | PTBC-002 | Present in workbook | Whether an authorized fast-track rule allows Under Review to be skipped
TASK-050 | Build Milestone Management (WF-05 Backend) | P8 | W4 | PTBC-006 | Required workbook edit | Backend enforcement of the mandatory-evidence policy on milestone achievement
TASK-051 | Build Milestone Register & Achievement UI (WF-05 Frontend) | P8 | W4 | PTBC-006 | Present in workbook | Evidence mandatory per milestone category; until resolved the UI labels evidence optional-pending-policy
TASK-051 | Build Milestone Register & Achievement UI (WF-05 Frontend) | P8 | W4 | PTBC-019 | Present in workbook | Cited jointly with PTBC-006 as a single precondition on the same acceptance criterion
TASK-052 | Build Financial Progress & KPI Performance (WF-14 Backend) | P8 | W3 | PTBC-024 | Required workbook edit | KPI target versions and formulas; measurements pin the version effective when recorded
TASK-052 | Build Financial Progress & KPI Performance (WF-14 Backend) | P8 | W3 | PTBC-025 | Required workbook edit | Financial condition and variance thresholds over stored figures
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | PTBC-024 | Required workbook edit | KPI status rendering depends on the approved targets
TASK-053 | Build Financial & KPI UI (WF-14 Frontend) | P8 | W3 | PTBC-025 | Required workbook edit | Financial condition indicator depends on the approved thresholds
TASK-055 | Build Risk Management (WF-06 Backend) | P9 | W3 | PTBC-017 | Present in workbook | Versioned probability/impact matrix used to compute a risk rating
TASK-056 | Build Risk Register & Detail UI (WF-06 Frontend) | P9 | W3 | PTBC-017 | Required workbook edit | The 5x5 heat-map renders the published matrix, never a hardcoded one
TASK-057 | Build Issue & Challenge Management (WF-07 Backend) | P9 | W3 | PTBC-017 | Required workbook edit | Issues use the same multi-dimensional five-level impact scale as risks (ADR-011)
TASK-059 | Contract & Regression Tests for Risk/Issue Domain (WF-06/07) | P9 | W3 | PTBC-017 | Required workbook edit | Regression test that assessment ratings stay pinned to the matrix version at assessment time
TASK-060 | Build Change Request & Authorization (WF-08 Backend) | P10 | W4 | PTBC-009 | Required workbook edit | Materiality evaluation and the resulting approval route
TASK-061 | Build Change Request UI (WF-08 Frontend) | P10 | W4 | PTBC-009 | Required workbook edit | Materiality classification shown to the requester before submission
TASK-066 | Build External Entity Update & Review (WF-13 Backend) | P11 | W5 | PTBC-003 | Required workbook edit | Which external entities are eligible and who authorises their participation
TASK-067 | Build External Participation UI (WF-13 Frontend) | P11 | W5 | PTBC-003 | Required workbook edit | External workspace scope follows the eligibility and authority decision
TASK-068 | Integrate Nafath Identity Verification (If Confirmed In Scope) | P11 | W5 | PTBC-003 | Present in workbook | External eligibility and onboarding authority
TASK-068 | Integrate Nafath Identity Verification (If Confirmed In Scope) | P11 | W5 | PTBC-031 | Present in workbook | Nafath use case and the identity attributes stored
TASK-073 | Build Formal Audit & Activity Service (FG-06 Backend) | P13 | W1 | PTBC-011 | Required workbook edit | The formal audit store captures the mandatory audit classes; append-only, not backfillable
TASK-075 | Build Integration Monitoring Runtime (FG-05 Backend) | P13 | W2 | PTBC-037 | Required workbook edit | Operational Alert raising depends on the availability, freshness and mismatch thresholds
TASK-083 | Implement Logging Redaction & Sensitive-Data Handling Policy | P14 | W1 | PTBC-029 | Required workbook edit | Redaction policy is drawn at the Audit/Log/SIEM boundary that PTBC-029 defines
TASK-084 | Author Platform Test Strategy & Coverage Policy | P15 | W1 | PTBC-040 | Required workbook edit | The accessibility test layer is scored against the conformance level
TASK-084 | Author Platform Test Strategy & Coverage Policy | P15 | W1 | PTBC-043 | Required workbook edit | The non-functional test layer is scored against the NFR thresholds
TASK-086 | Execute Performance & Load Testing Against Capacity Targets | P15 | W6 | PTBC-043 | Present in workbook | p95 latency pass-fail thresholds and the concurrency figures
TASK-087 | Execute Platform-Wide Accessibility Audit | P15 | W6 | PTBC-040 | Present in workbook | Conformance level the audit is scored against
TASK-091 | Implement Health Checks & Uptime Monitoring | P16 | W6 | PTBC-037 | Required workbook edit | Uptime alert threshold and window
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W6 | PTBC-037 | Present in workbook | Availability, freshness, queue backlog and reconciliation mismatch thresholds
TASK-092 | Build Operational Dashboards & Alerting Thresholds (FG-05 Alerts) | P16 | W6 | PTBC-046 | Present in workbook | Cited jointly with PTBC-037 as a single precondition
TASK-093 | Document Operational SLAs & On-Call Runbook | P16 | W6 | PTBC-048 | Required workbook edit | RPO 1 hour and RTO 4 to 6 hours are fixed inputs to the runbook; retention still open
TASK-106 | Build Change Materiality Band Routing | P4 | not assigned (task added after TASK-003) | PTBC-009 | Required workbook edit | Band boundary values for cost, schedule and scope routing

## Source TBC Crosswalk
Source TBC ID | Owning domain | Subject (as stated in the workbook) | PTBC theme | Resolution gate | Status | Resolution / decision on record | Evidence
TBC-IAM-002 | FG-03 Identity & Access | Permission profile composition from the protected FG-03 permission catalogue | PENDING - the 511 to 48 crosswalk requires Blueprint v2.0 Appendix F.2 and the Step 14B RTM | Before Build/Integration Build | Resolved | Configurable permission profiles authored, versioned, published and activated in FG-04; R01-R08 remain undeletable shipped defaults (ADR-018, 20 Sep 2026) | TASK-110 Validation Checks: "Resolves TBC-IAM-002, TBC-IAM-020 and TBC-CFG-019"
TBC-IAM-020 | FG-03 Identity & Access | Binding a user assignment to a permission profile version and explicit migration | PENDING - the 511 to 48 crosswalk requires Blueprint v2.0 Appendix F.2 and the Step 14B RTM | Before Build/Integration Build | Resolved | Assignments bind to a profile VERSION; migration to a newer version is explicit (ADR-018) | TASK-110 Validation Checks
TBC-CFG-019 | FG-04 Master Data & Configuration | Author/reviewer/publisher separation on profile publication | PENDING - the 511 to 48 crosswalk requires Blueprint v2.0 Appendix F.2 and the Step 14B RTM | Before Build/Integration Build | Resolved | FG-04 owns profile authoring, versioning, publication and activation with role separation (ADR-018) | TASK-110 Validation Checks; TASK-034 Participation Amendment
TBC-DSH-012 | FG-01 Dashboards | User personalization of published dashboards | PENDING - the 511 to 48 crosswalk requires Blueprint v2.0 Appendix F.2 and the Step 14B RTM | Before Build/Integration Build | Resolved | Show/hide/reorder of OptionalVisibility widgets, gated behind a Personalize Layout permission for R02, R03 and R07; presentation only (ADR-019, 20 Sep 2026) | TASK-111 Validation Checks: "Resolves TBC-DSH-012"
TBC-RPT-01 | FG-02 Reports | Report composition scope | PENDING - the 511 to 48 crosswalk requires Blueprint v2.0 Appendix F.2 and the Step 14B RTM | Before Build/Integration Build | Partially Resolved | Partly resolved by the SCR-138 controlled allowlisted explorer (ADR-019). Remainder not stated in the workbook | TASK-112 Validation Checks: "Resolves TBC-RPT-20 and part of TBC-RPT-01/03"
TBC-RPT-03 | FG-02 Reports | Report composition scope | PENDING - the 511 to 48 crosswalk requires Blueprint v2.0 Appendix F.2 and the Step 14B RTM | Before Build/Integration Build | Partially Resolved | Partly resolved by the SCR-138 controlled allowlisted explorer (ADR-019). Remainder not stated in the workbook | TASK-112 Validation Checks
TBC-RPT-20 | FG-02 Reports | Shared saved views | PENDING - the 511 to 48 crosswalk requires Blueprint v2.0 Appendix F.2 and the Step 14B RTM | Before Build/Integration Build | Resolved | Shared saved views enabled - configuration transfers, authorisation does not; every viewer is authorised independently at execution (ADR-019) | TASK-112 Validation Checks; TASK-072 Participation Amendment
TBC-RPT-26 | FG-02 Reports | External entity report and export entitlement | PENDING - the 511 to 48 crosswalk requires Blueprint v2.0 Appendix F.2 and the Step 14B RTM | Before Build/Integration Build | Resolved | External entity users receive the Project Dashboard for their own projects and nothing further - no report composition, no saved views, no export (ADR-019, superseding the 19 Sep position) | TASK-067 Participation Amendment

## Unassigned Gated Values
ID | Gated value | Proposed resolution gate | Gate basis | Decision owner | Affected tasks | Evidence | Why it is not on the PTBC register
UGV-01 | Data sensitivity and field-level classification taxonomy | Before Build/Integration Build | Field-level masking applies to every screen, dashboard, report, export and API projection; ADR-010 states that deciding late forces a revisit of every projection | AHDA Cybersecurity + PMO | TASK-029, TASK-030, TASK-052, TASK-053, TASK-083 | ADR-010 Status: "Approved (AHDA gate, 19 Sep 2026) - taxonomy outstanding"; TASK-029, TASK-083 Gate Decision Applied | No PTBC ID is cited anywhere for this value
UGV-02 | Project-level progress override tolerance | Before UAT | The override mechanism is built and flags the overridden figure; the tolerance is the scoring value | AHDA PMO | TASK-044 | TASK-044 Gate Decision Applied: "Override tolerance still TBC" | No PTBC ID and no Open Question row
UGV-03 | Notification channel scope per event family | Before UAT | ADR-004 enables SMS at launch; the event-to-channel, recipient-role and Mandatory/User-configurable matrices are FG-04 configuration AHDA populates | AHDA PMO / AHDA IT | TASK-034, TASK-039, TASK-040, TASK-103 | TASK-039 Detailed Description cites "SMS Conditional/TBC per PTBC" with no ID; ADR-004 | Dangling PTBC reference with no identifier
UGV-04 | Governance profile assignment thresholds (budget and duration) | Before UAT | Profile values are FG-04 configuration editable without a release; the assignment rule is the gated value | AHDA PMO | TASK-042, TASK-105 | TASK-105 Validation Checks: "Blocked on OQ-014 for the assignment thresholds" | OQ-014 is cited but has no row in the Open Questions sheet
UGV-05 | Change materiality band values | Before UAT | Mapped to PTBC-009, whose subject in OQ-005 is materiality/monetary thresholds - confirm against Appendix F.2 | AHDA Business Sponsor / Portfolio Office | TASK-027, TASK-034, TASK-106 | TASK-106 Validation Checks: "Blocked on OQ-013 for the values" | OQ-013 is cited but has no row in the Open Questions sheet; proposed mapping to PTBC-009
UGV-06 | Contractual SLA table for the ~22-month operations period | Before Production | Role-based structure is documented now; the numbers are contractual and do not affect build or functional UAT | AHDA Contracts / PMO Engagement Lead | TASK-093, TASK-097 | OQ-009; TASK-093 Gate Decision Applied | No PTBC ID
UGV-07 | GCP in-Kingdom region name and tenancy ownership | Before Build/Integration Build | Required before the first terraform apply; the region cannot be changed after provisioning without rebuilding every environment | AHDA IT | TASK-016, TASK-017 | ADR-001 Status: "written confirmation and region naming outstanding"; TASK-017 Gate Decision Applied | No PTBC ID; residual of OQ-001
UGV-08 | Legacy project-records source system, format, volume and field mapping | Before Production | Cutover is the last step; the mapping is needed before the migration rehearsal, not before build | AHDA IT / Data Owner | TASK-089, TASK-102 | OQ-008 Status: Blocked | No PTBC ID
UGV-09 | Dashboard and report contracted counting basis | Before Build/Integration Build | Fixes FG-01/FG-02 sizing before the definition catalogue is built | PMO Engagement Lead / AHDA Contracts | TASK-069, TASK-070, TASK-071, TASK-072 | OQ-002 (re-opened 19 Sep 2026); OQ-011; ADR-006 | No PTBC ID; count itself is fixed at 3 dashboards and 10 reports by ADR-006
UGV-10 | SMS provider selection and CST sender ID registration | Before UAT | Adapters are not interchangeable and sender ID registration takes about two weeks; only sandbox testing is possible until it completes | AHDA IT / PMO (provider); AHDA Contracts (commercial holder) | TASK-013, TASK-039, TASK-103 | OQ-012 | No PTBC ID
UGV-11 | Disposition of the 32 Step 14B RTM inventory-only components | Before Build/Integration Build | A component with no trace to a rank 1-3 source is not in the build list; the per-component decision is needed before the frontend tasks consume the inventory | PMO Engagement Lead | TASK-002 (F-04); all WF/FG frontend tasks | OQ-004; docs/rtm/step-14b-rtm-findings-closure.md F-04 | No PTBC ID